VMS “Phish-Guard” Project

Sprint Review Packet — Sprint 3

Sprint 3 Review and Project Status Update

| Project | VMS “Phish-Guard” Advanced Phishing Simulation & Training Portal |
| --- | --- |
| Client | Dr. James Barker |
| Project Manager | Kamira Sherman |
| Sprint Period | Sprint 3 (August 30 – September 13, 2026) |
| Report Date | September 13, 2026 |

# Executive Summary

Sprint 3 completed the remaining implementation-phase backlog and closed out the VMS “Phish-Guard” build. The team delivered role-based access control, the phishing-awareness quiz, the reporting dashboard, phishing landing pages and email templates, event tracking, privacy-preserving click tracking, the education-module redirect workflow, and the remaining security and governance documentation (third-party API validation controls, SSTI mitigation, AI security considerations, and secure media-upload validation). All ten Sprint 3 technical and governance backlog items (PB-02 through PB-21) were confirmed Done directly against the Jira board. The sprint also completed a client-authorized simulated-user pilot and formally retired the original Node.js/TypeScript/Express/Prisma technical plan in favor of the delivered Python/Flask/SQLite implementation.

# Sprint Objectives

- Complete the remaining core-platform backlog: access controls, quiz, reporting dashboard, landing pages, event tracking, email delivery

- Finalize security and governance documentation: SSTI mitigation, AI security considerations, third-party API validation, secure media-upload validation

- Obtain client authorization for, and complete, a simulated-user pilot

- Finalize project documentation and prepare the final handoff portfolio

# Completed Deliverables

## Core Platform

- PB-02 Role-based access controls

- PB-10 Phishing awareness quiz

- PB-07 Reporting dashboard

- PB-05 Phishing landing pages

- PB-04 Phishing email templates

- PB-13 Email delivery integration

- PB-12 Event tracking capabilities

- PB-06 Privacy-preserving click tracking

- PB-09 Education-module redirect workflow

- PB-21 Secure media-upload validation

## Governance and Security

- PB-14 Third-party API validation controls

- PB-15 SSTI mitigation assessment

- PB-16 AI security considerations documentation

- PB-22 Retirement of the Node.js/TypeScript/Express/Prisma technical plan; documentation aligned to the delivered Flask/SQLite implementation

## Client Communication

- September 2 sprint recap (missed live meeting) covering Sprint 2 close-out and Sprint 3 in-progress status

- September 6–7 email exchange authorizing simulated-user pilot testing

# Backlog and Scope Updates

All ten Sprint 3 technical and governance backlog items (PB-02 through PB-21) reached Done status, confirmed directly against the Jira board on September 15, 2026. No scope changes occurred during Sprint 3; the project remained aligned with the approved Phish-Guard vision, objectives, and ethical requirements.

# Governance and Security Updates

With Dr. Barker's written authorization (September 6–7 email exchange), the team completed a small-group pilot using simulated, non-PII test data only, consistent with the Safe Data Handling Plan. The SSTI mitigation assessment and AI security considerations documentation were finalized, and third-party API validation controls and secure media-upload validation were implemented and verified.

# Current Risks and Challenges

## Client Availability

Dr. Barker was unable to attend the September 2 review. Mitigation: the team proceeded with its internal sprint meeting and sent a same-day written recap; the client's response arrived outside the standard 48-hour window but confirmed no additional scope changes.

## Project Close-Out

With all backlog items complete, remaining risk shifted to documentation organization and handoff quality. Mitigation: the final handoff portfolio was assembled and organized by section (governance, agile planning, security, technical, client communication) to reduce onboarding friction for any future team.

# Agile Insights and Lessons Learned

- Completing access control and the quiz early in the sprint created capacity to finish the reporting dashboard and landing pages without schedule pressure.

- Confirming client authorization in writing before pilot testing kept the ethical data-handling boundary explicit and auditable.

- Closing the backlog against the Jira board, not a status list, gave the team and client a verifiable single source of truth at project close.

- Formally retiring the earlier Node.js/TypeScript/Express/Prisma plan in the Decision Log prevented stale documentation from surviving into the handoff package.

- Consistent asynchronous communication carried the project through a second missed live meeting without losing client alignment.

# Transition and Handoff Strategy

With Sprint 3 complete, the team organized all project artifacts into a structured handoff portfolio spanning governance, agile planning and traceability, security and compliance, technical/working software, and client communication. This preserves the reasoning behind key decisions, keeps requirements traceable to acceptance criteria and controls, and gives Dr. Barker (or any future team) a complete, organized record of the implementation phase.

# Client Feedback Requested

- Final review of the completed platform and reporting dashboard

- Any last scope or priority changes ahead of project close

- Feedback on the final handoff portfolio organization

# Overall Project Status

| Schedule Status | Complete |
| --- | --- |
| Scope Status | Complete |
| Governance Status | Complete |
| Documentation Status | Complete |
| Client Engagement Status | Active (Asynchronous Communication) |
| Backlog Status | All Sprint 3 Items (PB-02–PB-21) Confirmed Done |

# Next Steps

- Deliver the final handoff portfolio to Dr. Barker

- Complete the Week 10 comprehensive handoff report

- Maintain documentation for any future project phase

- Close out the project on schedule