## Dependency Matrix
Component / Workstream | Depends On | Dependency Description | Risk if Delayed | Mitigation Strategy | Owner | Status
Reporting Dashboard | Event Tracking Logic | Dashboard metrics require validated interaction-event data | Reports may display incomplete or inaccurate metrics | Finalize event-tracking requirements before dashboard implementation | Frontend / Backend | completed
Training Module | Landing Page Workflow | Training content triggers after simulated interaction | Users may not reach awareness content correctly | Validate post-click workflow before training integration | Security Content Team | completed
Event Tracking | Safe Data Handling Plan | Tracking logic must follow privacy-preserving data rules | Risk of collecting prohibited or excessive data | Review all tracking fields against governance requirements | Backend Team | completed
Role-Based Access Control | Backend Authentication Logic | Administrative permissions depend on authentication workflows | Unauthorized access to admin functionality | Validate RBAC requirements before implementation | Backend Team | completed
Database Schema Concepts | Data Minimization Rules | Database structure depends on approved data categories | Schema redesign or excessive data collection risk | Finalize approved data inventory before schema planning | Backend / Governance | completed
Audit Logging | API Workflow Requirements | Logging structure depends on endpoint activity definitions | Incomplete audit visibility or missing records | Document required log events during API planning | Backend Team | completed
Quiz Reporting Metrics | Training Module Completion Logic | Reporting depends on quiz and module completion tracking | Inaccurate awareness-training metrics | Define quiz completion events during workflow planning | Frontend / Reporting | completed
Client Sprint Reviews | Sprint Artifact Completion | Client feedback depends on completed deliverables and updates | Delayed stakeholder decisions and approvals | Prepare sprint review packet before meetings | Project Manager | Ongoing